## Sheet1
|  | Project Name: |  | EmployeePayrollManagement | Payroll Management
Daily Project Status Report
Backend /Database Part
Date | Name |  | Work
2022-02-14 | Ajay |  | Discussion On About project
2022-02-14 | Deepali |  | Discussion On About project
2022-02-14 | Krishna |  | Discussion On About project
2022-02-14 | Ravi |  | Discussion On About project
2022-02-14 | Diana Rani |  | Discussion On About project
2022-02-14 | Nagarani |  | Discussion On About project
2022-02-15 | Ajay |  | Discussion About Flow Chart And Database Schema
2022-02-15 | Deepali |  | Discussion About Flow Chart And Database Schema
2022-02-15 | Krishna |  | Discussion About Flow Chart And Database Schema
2022-02-15 | Ravi |  | Discussion About Flow Chart And Database Schema
2022-02-15 | Diana Rani |  | Discussion About Flow Chart And Database Schema
2022-02-15 | Nagarani |  | Discussion About Flow Chart And Database Schema
2022-02-16 | Ajay |  | Started doing Attendence Part
2022-02-16 | Deepali |  | Started doing Employee Part
2022-02-16 | Krishna |  | Started doing User And Admin Part
2022-02-16 | Ravi |  | Database Completed Schema
2022-02-16 | Diana Rani |  | Database Completed Schema
2022-02-16 | Nagarani |  | Database Completed Schema
2022-02-17 | Ajay |  | Working On Backend Errors
2022-02-17 | Deepali |  | Working On Backend Errors
2022-02-17 | Krishna |  | Working On Backend Errors
2022-02-17 | Ravi |  | Working On Backend Errors
2022-02-17 | Diana Rani |  | Working On Backend Errors
2022-02-17 | Nagarani |  | Working On Backend Errors
2022-02-18 | Ajay |  | Working on EmployeeAttendance Module
2022-02-18 | Deepali |  | Working on Update profile & Change Password
2022-02-18 | Krishna |  | Working on Admin login module
2022-02-18 | Ravi |  | Working on Add Employee ,Add Salary Module
2022-02-18 | Diana Rani |  | Working on Amin Leaves Module | n Admin | Leaves Module
2022-02-18 | Nagarani |  | Working on Employee Leaves Module
2022-02-19 | Ajay |  | Completed EmployeeAttendance Module
2022-02-19 | Deepali |  | Completed Update profile & Change Password
2022-02-19 | Krishna |  | Completed Admin login module
2022-02-19 | Ravi |  | Completed Add Employee ,Add Salary Module
2022-02-19 | Diana Rani |  | Completed Admin Leaves Module
2022-02-19 | Nagarani |  | Completed Employee Leaves Module
2022-02-21 | Ajay |  | Working Admin Attendance Junit test Cases
2022-02-21 | Deepali |  | Working Updateprofile Junit test Cases
2022-02-21 | Krishna |  | Working Employee Salary test Cases
2022-02-21 | Ravi |  | Working Add Employee ,Add Salary Module tests Cases
2022-02-21 | Diana Rani |  | Working Admin leaves test Cases
2022-02-21 | Nagarani |  | Working Employee leaves test Cases
2022-02-22 | Ajay |  | Working Admin Attendance Junit test Cases
2022-02-22 | Deepali |  | Working Updateprofile Junit test Cases
2022-02-22 | Krishna |  | Working Employee Salary test Cases
2022-02-22 | Ravi |  | Working Add Employee ,Add Salary Module tests Cases
2022-02-22 | Diana Rani |  | Working on PPT & Documentation
2022-02-22 | Nagarani |  | Working on PPT & Documentation
2022-02-23 | Ajay |  | Working Admin Attendance Junit test Cases
2022-02-23 | Deepali |  | Working Updateprofile Junit test Cases
2022-02-23 | Krishna |  | Working Employee Salary test Cases
2022-02-23 | Ravi |  | Working Add Employee ,Add Salary Module tests Cases
2022-02-23 | Dayana Rani |  | Working on PPT & Documentation
2022-02-23 | Nagarani |  | Working on PPT & Documentation
2022-02-24 | Ajay |  | Working Integration part
2022-02-24 | Deepali |  | Working Integration part
2022-02-24 | Krishna |  | Working Integration part
2022-02-24 | Ravi |  | Working Integration part
2022-02-24 | Dayana Rani |  | Completed on PPT & Documentation
2022-02-24 | Nagarani |  | Completed on PPT & Documentation
2022-02-25 | Ajay |  | joined meet for evaluation
2022-02-25 | Deepali |  | joined meet for evaluation
2022-02-25 | Krishna |  | joined meet for evaluation
2022-02-25 | Ravi |  | joined meet for evaluation
2022-02-25 | Dayana Rani |  | joined meet for evaluation
2022-02-25 | Nagarani |  | joined meet for evaluation
2022-02-26 | Ajay |  | started working on J unit testing
2022-02-26 | Deepali |  | started working on J unit testing
2022-02-26 | Krishna |  | started working on J unit testing
2022-02-26 | Ravi |  | started working on J unit testing
2022-02-26 | Dayana Rani |  | started working on J unit testing
2022-02-26 | Nagarani |  | started working on J unit testing
2022-02-27 | Ajay |  | Completed J unit testing module
2022-02-27 | Deepali |  | Completed J unit testing module
2022-02-27 | Krishna |  | Completed J unit testing module
2022-02-27 | Ravi |  | Completed J unit testing module
2022-02-27 | Dayana Rani |  | Completed J unit testing module
2022-02-27 | Nagarani |  | Completed J unit testing module
2022-02-28 | Ajay |  | joined meet
2022-02-28 | Deepali |  | joined meet
2022-02-28 | Krishna |  | joined meet
2022-02-28 | Ravi |  | joined meet
2022-02-28 | Dayana Rani |  | joined meet
2022-02-28 | Nagarani |  | joined meet